## FY24(DEV)
No | Main item | HC | Section | Progress | Target | Status | Plan/ Result | Date | Merit (K$) | HC | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | PIC ISD
1 | PEMS communicate current PSNV system (real time) |  | Manufacturing ALL |  |  |  | Original Plan | 2024-04-01 | [14 empty] | Phong, Minh | bar: Apr to Jun
[7 empty] | Adjusted Plan |  | 3.8 | [16 empty] | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
[7 empty] | Acrtual Result |  |  |  | 1 | [12 empty] | Costdown | Plan | [12 empty] | 4 | bar: Jun; Aug; Oct; Mar
[25 empty] | HC(pax) | Oct: 15; Mar: 2 | 17
2 | Upgrade new version for Android App |  | ISD,GA,PE,FA,SCS |  |  |  | Original Plan | 2024-04-01 |  |  | 1 | 1 | 1 | [9 empty] | Minh, Phong, T.Anh |  | AMT ($) | Jun: 3.8; Aug: 36.8 | 40.6
[7 empty] | Adjusted Plan | [16 empty] | Q'ty | Plan | Jun: 1; Aug: 1; Sep: 1; Jan: 2; Mar: 1 | 6
[7 empty] | Acrtual Result |  |  |  | 1 | [14 empty] | Mar: Total item | 10
3 | Smart warehouse management system |  | Procurement |  |  |  | Original Plan | 2024-04-01 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | Hien, Minh, Phong, T.Anh |  |  | Mar: AMT
[7 empty] | Adjusted Plan |  |  | 15
[7 empty] | Acrtual Result |  |  |  | 1
4 | E-leave control system |  | HR-GA |  |  |  | Original Plan | 2024-06-01 |  |  |  |  | 1 | 1 | 1 | 1 | [6 empty] | Hien, Minh, Phong, T.Anh
[7 empty] | Adjusted Plan |  | 36.8
Acrtual Result
5 | Traceability for DP new model: AE, EW |  | Manufacturing DP |  |  |  | Original Plan | 2024-06-01 |  |  |  |  | 1 | 1 | 1 | [7 empty] | Hien, Phong
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
|  |  |  | 50 |  |  | Original Plan
Adjusted Plan
Acrtual Result
6 | Prohibited software detect |  | ISD |  |  |  | Original Plan | 2024-08-01 | [6 empty] | 1 | 1 | [6 empty] | Hien
Adjusted Plan
Acrtual Result
7 | Add verify serial numbers of product<DP> |  | Manufacturing DP |  |  |  | Original Plan | 2024-10-01 | [8 empty] | 1 | 1 | 1 | 1 |  |  | Phong, T.Anh
Adjusted Plan
Acrtual Result
8 | Make weight check to strictly control packing |  | Manufacturing MCW |  |  |  | Original Plan | 2024-11-01 | [9 empty] | 1 | 1 | 1 |  |  | Minh, T.Anh
Adjusted Plan
Acrtual Result
9 | Communicate OQC inspection FA-OQC-SCM |  | FA,OQC,SCM |  |  |  | Original Plan | 2024-12-01 | [10 empty] | 1 | 1 | 1 | 1 | Hien, Minh, Phong, T.Anh
[7 empty] | Adjusted Plan |  |  | 2
Acrtual Result
10 | Material daily shortage notification |  | MCS, PUS, FA, SMT |  |  |  | Original Plan | 2025-01-01 | [11 empty] | 1 | 1 | 1 | T.Anh
Adjusted Plan
Acrtual Result
TOTAL MERIT SUMMARY | [6 empty] | Original Plan |  | 40.6 | 18
Acrtual Result
Diff Amount
|  |  |  | plan: |  |  |  | FY24 | 40.6 | 108 |  | 148.6
|  |  |  | result |  |  |  | FY23 | 17.6 |  |  | 17.6
166.2
1. Input PIC
2. Cost down Pax ( worker / staff ?) : 17 pax
Worker : 500$/ month
Staff : 1K$/ Month
Manager : 3KS/ month
Jun Start

## Detai Schedule (hidden)
|  |  |  | Jun-22 |  |  |  | Jul-22 |  |  |  | Aug-22 |  |  |  | Sep-22 |  |  |  | Oct-22 |  |  |  | Nov-22 |  |  |  | Dec-22 |  |  |  | Jan-23 |  |  |  | Feb-23 |  |  |  | Mar-23
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Lam | 3 | PUS, PSCD | Shipping advice analysis | Jun-22 W1: Testing SA analysis & adjust program; Sep-22 W1: Develop Analysis and Vendor confirmation; Oct-22 W1: Test; Oct-22 W4: Golive
Lam & New | 3 | PUS, PSCD | Forecast report | Oct-22 W2: Studying; Oct-22 W4: collect data & make FS; Nov-22 W2: develop; Dec-22 W3: Testing; Jan-23 W2: Adjust; Jan-23 W4: Golive
SAP | 11 | ACD, PSCD | e-Invoice : Send Invoice to FPT server (Call API) | Jun-22 W1: Collect SAP data (New Packing/invoice); Jun-22 W4: Collect data outside SAP (VN names, Unit); Jul-22 W3: request/ response to FPT; Aug-22 W1: - Test call API - PSNM active HTTP - Install certificates; Aug-22 W3: Golive